## Team 5
Tasks | Week 1 Mar30-Apr3 | Week 2 Apr6-10 | Week 3 Apr13-17 | Week 4 Apr20-24 | Week 5 Apr27-May1 | Week 6 May4-8
Capture user requirement using class diagram | 2
Analysis of feature 1 - Backend | 6 | 4
Analysis of feature 2 - Filter | 10 | 6
Analysis of feature 3 - List | 4
Analysis of feature 4 - Timetable | 6 | 12 | 9 | 3
Analysis of feature 5 - All Subject Search | 9 | 5
Analysis of feature 6 - SFQ | 3
Design of feature 1 - Backend | 3 | 3
Design of feature 2 - Filter | 4 | 4
Design of feature 3 - List | 3 | 3
Design of feature 4 - Timetable | 3 | 3 | 3 | 3
Design of feature 5 - All Subject Search | 4 | 4 | 1
Design of feature 6 - SFQ | 3 | 3 | 3 | 3
Code implementation feature 1 - Backend | 8 | 8 | 6
Code implementation feature 2 - Filter | 9 | 10 | 12 | 9
Code implementation feature 3 - List | 7 | 9 | 6 | 4
Code implementation feature 4 - Timetable | 8 | 8 | 10 | 8
Code implementation feature 5 - All Subject Search | 9 | 10 | 11 | 6
Code implementation feature 6 - SFQ | 8 | 8 | 8 | 8
Test and document Code implementation feature 1 - Backend | 4 | 4 | 4 | 4 | 4
Test and document Code implementation feature 2 - Filter | 3 | 3 | 3 | 5 | 3
Test and document Code implementation feature 3 - List | 3 | 4 | 4 | 4 | 3
Test and document Code implementation feature 4 - Timetable | 2 | 2 | 2 | 2 | 2
Test and document Code implementation feature 5 - All Subject Search | 4 | 4 | 4 | 5 | 5
Test and document Code implementation feature 6 - SFQ | 4 | 4 | 4 | 4 | 4
Total hours | 129 | 121 | 90 | 68 | 21 | 0
Task 4 & 6, completed by ZHOU Zhuorui | Week 1 Mar30-Apr3 | Week 2 Apr6-10 | Week 3 Apr13-17 | Week 4 Apr20-24 | Week 5 Apr27-May1 | Week 6 May4-8
Capture user requirement using class diagram | 2
Analysis of feature 4 - Timetable | 6 | 12 | 9 | 3
Analysis of feature 6 - SFQ | 3
Design of feature 4 - Timetable | 3 | 3 | 3 | 3
Design of feature 6 - SFQ | 3 | 3 | 3 | 3
Code implementation feature 4 - Timetable | 8 | 8 | 10 | 8
Code implementation feature 6 - SFQ | 8 | 8 | 8 | 8
Test and document Code implementation feature 4 - Timetable | 2 | 2 | 2 | 2 | 2
Test and document Code implementation feature 6 - SFQ | 4 | 4 | 4 | 4 | 4
Total hours | 39 | 40 | 39 | 31 | 6 | 0
Task 2 & 3, completed by Wui Wo TAM | Week 1 Mar30-Apr3 | Week 2 Apr6-10 | Week 3 Apr13-17 | Week 4 Apr20-24 | Week 5 Apr27-May1 | Week 6 May4-8
Capture user requirement using class diagram | 2
Analysis of feature 2 - Filter | 10 | 6
Analysis of feature 3 - List | 4
Design of feature 2 - Filter | 4 | 4
Design of feature 3 - List | 3 | 3
Code implementation feature 2 - Filter | 9 | 10 | 12 | 10
Code implementation feature 3 - List | 7 | 9 | 6 | 9 | 2
Test and document Code implementation feature 2 - Filter | 3 | 3 | 3 | 5 | 3
Test and document Code implementation feature 3 - List | 3 | 4 | 4 | 4 | 3
Total hours | 45 | 39 | 25 | 28 | 8 | 0
Task 1 & 5, completed by YAP Zhi Yun | Week 1 Mar30-Apr3 | Week 2 Apr6-10 | Week 3 Apr13-17 | Week 4 Apr20-24 | Week 5 Apr27-May1 | Week 6 May4-8
Capture user requirement using class diagram | 2
Analysis of feature 1 - Backend | 6 | 4
Analysis of feature 5 - All Subject Search | 9 | 5
Design of feature 1 - Backend | 3 | 3
Design of feature 5 - All Subject Search | 4 | 4 | 1
Code implementation feature 1 - Backend | 8 | 8 | 6
Code implementation feature 5 - All Subject Search | 9 | 10 | 11 | 6
Test and document Code implementation feature 1 - Backend | 4 | 4 | 4 | 4 | 4
Test and document Code implementation feature 5 - All Subject Search | 4 | 4 | 4 | 5 | 5
Total hours | 49 | 42 | 26 | 15 | 9 | 0