## Team05
Tasks | Week 1 Mar30-Apr3 | Week 2 Apr6-10 | Week 3 Apr13-17 | Week 4 Apr20-24 | Week 5 Apr27-May1 | Week 6 May4-8
Capture user requirement using class diagram | 2
Design implementation of feature 1 - Backend | 3 | 3
Design implementation of feature 2 - Filter | 4 | 4
Design implementation of feature 3 - List | 3 | 3
Design implementation of feature 4 - Timetable | 3 | 3
Design implementation of feature 5 - All Subject Search | 4 | 4 | 1
Design implementation of feature 6 - SFQ | 3 | 3 | 3
Code for feature 1 - Backend | 8 | 8 | 6
Code for feature 2 - Filter | 9 | 10 | 12 | 9
Code for feature 3 - List | 7 | 9 | 6 | 4
Code for feature 4 - Timetable | 8 | 8 | 10 | 8
Code for feature 5 - All Subject Search | 9 | 10 | 11 | 6
Code for feature 6 - SFQ | 8 | 8 | 8 | 8
Test and document code for feature 1 - Backend | 4 | 4 | 4 | 4 | 4
Test and document code for feature 2 - Filter | 3 | 3 | 3 | 5 | 3
Test and document code for feature 3 - List | 3 | 4 | 4 | 4 | 3
Test and document code for feature 4 - Timetable | 2 | 2 | 2 | 2 | 2
Test and document code for feature 5 - All Subject Search | 4 | 4 | 4 | 5 | 5
Test and document code for feature 6 - SFQ | 4 | 4 | 4 | 4 | 4
Document code for feature 1 - Backend
Document code for feature 2 - Filter
Document code for feature 3 - List
Document code for feature
Total hours | 91 | 94 | 78 | 59 | 21 | 0